# Move of ALPHA II and Bloor Collegiate Institute to Central Technical School Beginning September 2021 – Timeline

| **Completed** | **Current** | **Near Term** | **Future** |
| --- | --- | --- | --- |
| After meetings of the Area Review Committee, Board recommends that Kent Senior Public School be closed and ALPHA II relocated to Bloor CI: June 23, 2010 | Updates of move to Central Tech provided at each Bloor CI Parent Council Zoom meeting and ALPHA II Community Meetings | Renovations at Central Tech complete: June 2021 | Awaiting Ministry approval to tender for the construction of the new school for ALPHA II and BCI at the Brockton site |
| Local School Community Design Team (LSCDT) meets to receive Master Plan for Bloor Dufferin Site from Sweeny Sterline Finlayson & Co Architects Inc. including new school at Brockton site: May 29,  2012 | Joint website of ALPHA II, BCI and CTS with frequently asked questions goes online: April 28, 2021 | Virtual Tours of new space at CTS conducted: June, 2021 | TDSB submits application to the City of Toronto for Notice of Conditional of Approval for Site Plan Approval of the new school at the Brockton site |
| Building a Better Bloor Dufferin (BBBD), a coalition of local residents, business, community, education and arts groups has long advocated that any development at Bloor Dufferin should include more parkland, a new school, community space, daycare and deeply affordable housing. formed in 2014 | Advertising to inform parents and students of the three schools of the new website: May, 2021 | TDSB required to vacate BCI building and empty all contents: July 31, 2021 | City of Toronto grants Notice of Conditional Approval (NOAC) to begin construction of new school at Brockton site |
| Toronto Lands Corporation assesses offers to Purchase for the Bloor Dufferin site: April 18, 2014 | Walk-through video of CTS created to be sent to BCI and ALPHA II families, Spring, 2021 | Final preparations regarding move of ALPHA II and BCI to 3rd floor of CTS | Final TDSB approval to begin construction of new school at Brockton site |
| Bloor-Dufferin TDSB Lands Community Meeting calls for community hub: June 20, 2016 | Welcome letter and video to go to families of the three schools: Aug., 2021 | Final preparations regarding move of ALPHA II and BCI to 3rd floor of CTS | TDSB issues Project for Tender for new school building |
| TDSB approves sale of the Bloor-Dufferin property to Capital Developments for $120 million 2017 | Family orientations—in person or online if COVID restrictions continue: Sept., 2021 | Final preparations regarding move of ALPHA II and BCI to 3rd floor of CTS | Building permit issued by the City of Toronto for the new school |
| Original plan to move ALPHA II and BCI students to a deep retrofitted Brockton High School, TDSB concluded a retrofit of Brockton would not meet needs. TDSB approves new building: Spring, 2017 | BCI and ALPHA II students begin the school year at CTS: Sept, 2021 | Final preparations regarding move of ALPHA II and BCI to 3rd floor of CTS | Construction of the new school: Summer 2021-Summer 2023 |
| Change in Ontario Government to Conservative, new team at Ministry of Education: June,  2018 | BCI and ALPHA II students begin the school year at CTS: Sept, 2021 | Final preparations regarding move of ALPHA II and BCI to 3rd floor of CTS | ALPHA II and BCI move to new school building on Brockton site: Fall 2023 |
| Design finalized by Snyder Architects to accommodate 924 pupils, with possible expansion to accommodate 1,200 pupils, budgeted cost $34 million funded by a Ministry of Education grant and TDSB proceeds of disposition: March, 2019 | BCI and ALPHA II students begin the school year at CTS: Sept, 2021 | Final preparations regarding move of ALPHA II and BCI to 3rd floor of CTS | ALPHA II and BCI move to new school building on Brockton site: Fall 2023 |
| Demolition of Brockton Complete: May, 2019 | BCI and ALPHA II students begin the school year at CTS: Sept, 2021 | Final preparations regarding move of ALPHA II and BCI to 3rd floor of CTS | ALPHA II and BCI move to new school building on Brockton site: Fall 2023 |
| Plan to relocate to CTS for 2020-21 school year announced: Spring,  2019 | BCI and ALPHA II students begin the school year at CTS: Sept, 2021 | Final preparations regarding move of ALPHA II and BCI to 3rd floor of CTS | ALPHA II and BCI move to new school building on Brockton site: Fall 2023 |
| Move to CTS delayed by one year as developer requests extension: Nov., 2019 | BCI and ALPHA II students begin the school year at CTS: Sept, 2021 | Final preparations regarding move of ALPHA II and BCI to 3rd floor of CTS | ALPHA II and BCI move to new school building on Brockton site: Fall 2023 |
| BBBD negotiates historic $17 million land trust seeded by Toronto developers Capital Developments and Metropia to create new affordable housing for Toronto residents. The land trust is the result of a collaboration between Toronto development companies, the City of Toronto, Habitat for Humanity GTA, St. Clare’s Multifaith homes. November 2019 | BCI and ALPHA II students begin the school year at CTS: Sept, 2021 | Final preparations regarding move of ALPHA II and BCI to 3rd floor of CTS | ALPHA II and BCI move to new school building on Brockton site: Fall 2023 |
| Pandemic halts project: Feb., 2020 | BCI and ALPHA II students begin the school year at CTS: Sept, 2021 | Final preparations regarding move of ALPHA II and BCI to 3rd floor of CTS | ALPHA II and BCI move to new school building on Brockton site: Fall 2023 |